## Start Here
HRMS Progress Workbook — operating instructions
This workbook is dynamic: update feature rows in Master Feature Tracker. Dashboards, module rollups and readiness views recalculate automatically.
Step | Where | What to update | How it works
1 | Master Feature Tracker | Layer percentages (UI/API/DB/Rules/Security/Integration/QA/Docs) | Choose 0/25/50/75/100. Auto % averages the eight evidence layers.
2 | Master Feature Tracker | Progress Mode + Manual % | Auto uses layer scores; switch to Manual to use your approved Manual % instead.
3 | Master Feature Tracker | Status, readiness, priority, risk, owner, dates, release | Dropdowns are editable reference lists; all summary sheets respond to the tracker.
4 | Definitions Dropdowns | Any dropdown list | Add or rename list values; then use the tracker dropdowns for consistent reporting.
5 | Module Summary / Dashboard | Read the outcome | These are formula views. Do not enter progress here; edit the tracker row.
6 | Change Log | Every material update | Record date, author, reason, evidence and follow-up for auditability.
Baseline meaning: populated values show code/documentation footprint and are not claims of runtime or production validation. Rows flagged “Documented - Not Runtime Verified” require evidence before production readiness is set.

## Dashboard
HRMS Delivery Dashboard — live formulas from Master Feature Tracker
Effective progress |  | Tracked items |  | Blocked |  | Needs QA |  | Critical risk |  | Production ready
55 |  | 68 |  | 0 |  | 68 |  | 4 |  | 0
Status | Count | Readiness | Count |  | Priority | Count | Overdue | Count | Action Required
Not Started | 0 | Not Ready | 0 |  | Critical | 21 | Overdue (open) | 0 | Assign owner + target date
Planned | 0 | In Build | 0 |  | High | 36 |  |  | Set layer scores or manual %
In Progress | 68 | Needs QA | 68 |  | Medium | 11 |  |  | Attach runtime evidence
Blocked | 0 | Pilot Ready | 0 |  | Low | 0 |  |  | Resolve blocker before release
Ready for QA | 0 | Production Ready | 0
Done | 0
Deferred | 0
Operating rule: update Master Feature Tracker only; it is the source of truth. Do not label a row Production Ready unless runtime evidence and release validation are attached.

## Master Feature Tracker
Master Feature Tracker — live, feature-level delivery control
Feature ID | Domain | Module | Feature | Sub-feature / Deliverable | Current Flow / Scope | Evidence / Source | Feature Type | UI % | API % | DB % | Rules % | Security % | Integration % | QA % | Docs % | Auto % | Manual % | Progress Mode | Effective % | Status | Readiness | Priority | Risk | Owner | Start Date | Target Date | Release | Dependency / Blocker | Next Action | Technical Debt / Gap | Verification | Updated On | Notes
HRMS-001 | Platform & Access | Platform & Access | Authentication | Login and token issue | JWT login and refresh-token lifecycle | AccountController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-002 | Platform & Access | Platform & Access | Authentication | Password recovery | Forgot password, reset and first-time password | AccountController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-003 | Platform & Access | Platform & Access | Authentication | Registration | New company + administrator registration | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-004 | Platform & Access | Platform & Access | Authorization | Role and module permissions | Role/module feature permission gates | RolesController.cs; CMS-React/docs/routing-and-auth.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-005 | Platform & Access | Platform & Access | Authorization | Route protection | Protected routes and parent-route guard review | CMS-React/docs/routing-and-auth.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-006 | Company & Tenant | Company & Tenant | Company management | Company profile | Tenant company profile / active state | CompanyController.cs; CompanyService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-007 | Company & Tenant | Company & Tenant | Company management | Company master | Company master setup and administration | CompanyMasterController.cs; CompanyMasterService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-008 | Company & Tenant | Company & Tenant | Tenant isolation | Company context enforcement | Tenant-scoped server data and JWT company claim | backend README.md; doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | Critical | Unassigned |  |  |  | Isolated integration proof required | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-009 | Company & Tenant | Company & Tenant | Company configuration | Application modules | Admin company module area / configuration seam | CMS-React/docs/routing-and-auth.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-010 | Employees | Employees | Employee directory | Employee listing and filters | Search, headcount, employee list | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-011 | Employees | Employees | Employee lifecycle | Invite employee | Multi-step employee invite flow | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-012 | Employees | Employees | Employee profile | Personal and employment profile | Self and HR/admin employee profile scopes | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-013 | Employees | Employees | Employee profile | Education and certification | Employee profile supporting records | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Low | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-014 | Employees | Employees | Employee lifecycle | Employment status | Active / exit / rejoin employment state | EmployeeService.cs; README_OFFBOARDING_FIXES.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-015 | Leave | Leave | Leave configuration | Leave policy and types | Leave policies, types and accrual configuration | LeaveManagementController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-016 | Leave | Leave | Leave requests | Request submission | Submit, list and withdraw leave requests | LeaveManagementController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-017 | Leave | Leave | Leave approvals | Approval and rejection | Approval workflow and balance/reconciliation impacts | LeaveManagementService.cs; backend doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-018 | Leave | Leave | Leave balances | Balance and accrual | Accrual and balance calculations | LeaveAccrualHostedService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-019 | Leave | Leave | Leave / WFH coordination | Overlap prevention | Cross-check active WFH and leave requests | LeaveManagementService.cs; WorkFromHomeService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-020 | Attendance | Attendance | Daily attendance | Check-in / check-out | Daily employee presence and time records | AttendanceService.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-021 | Attendance | Attendance | Attendance calendar | Monthly view | Calendar, status and attendance details | MyAttendanceController.cs; AttendanceCalendar.tsx | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-022 | Attendance | Attendance | Attendance administration | Manual edit and correction | Admin update + employee correction request | AttendanceController.cs; MyAttendanceController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-023 | Attendance | Attendance | Attendance ownership | Source-owned records | Protect WFH/leave-created attendance from generic edit | WorkFromHomeService.cs; memory evidence | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | Critical | Unassigned |  |  |  | Isolated integration proof required | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-024 | Attendance | Attendance | Attendance readiness | Month lock validation | Lock status and payroll-readiness validation | AttendancePenaltyController.cs; AttendancePayrollReadinessService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-025 | Attendance | Attendance | Attendance operations | Monthly initialize / export | Initialize-month and monthly export | AttendanceController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-026 | Attendance | Attendance | Attendance policy | Status settings and penalties | Status configuration, penalties and exception resolution | AttendanceStatusSettingsController.cs; AttendancePenaltyController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-027 | Work From Home | Work From Home | WFH requests | Request lifecycle | Create, manager/team/all retrieval and cancellation | WorkFromHomeController.cs; WorkFromHomeService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-028 | Work From Home | Work From Home | WFH approvals | Version-checked decision | Approval/rejection with version checks | WorkFromHomeService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-029 | Work From Home | Work From Home | WFH attendance | Source-linked reconciliation | Attendance update and conflict exceptions | WorkFromHomeService.cs; LeaveAttendanceReconciliationService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-030 | Work From Home | Work From Home | WFH policy | Policy and audit | Policy, audit/request log and structured remarks | WorkFromHomeService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-031 | Work From Home | Work From Home | WFH half-day | Half-day attendance segments | Segment / time boundary validation | WorkFromHomeService.cs; memory evidence | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-032 | Payroll | Payroll | Salary | Salary history and active record | Salary CRUD, active salary and history | SalaryController.cs; SalaryService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-033 | Payroll | Payroll | Payroll setup | Salary structure and deductions | Company-wide structure, tax and deduction settings | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-034 | Payroll | Payroll | Payroll settings | Payroll divisor policy | View/edit company divisor policy | PayrollDivisorPolicyController.cs; PayrollDivisorPolicyService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-035 | Payroll | Payroll | Payroll processing | Period generation | Monthly processing and employee payroll generation | PayRollController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-036 | Payroll | Payroll | Payroll controls | Locked attendance dependency | Attendance readiness before payroll | AttendancePayrollReadinessService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-037 | Payroll | Payroll | Payslips | PDF preview/download | Generated payslip/document output | PayRollController.cs; PdfService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-038 | Payroll | Payroll | Payroll import | Upload workflow | Payroll upload path and input sanitization review | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-039 | Recruitment | Recruitment | Vacancies | Job vacancy CRUD | Create/view/edit/delete vacancy | JobVacancyController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-040 | Recruitment | Recruitment | Applicants | Applicant intake | Add/list/edit applications and resumes | ApplicantsController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-041 | Recruitment | Recruitment | Applicant workflow | Pipeline status changes | New through selection/rejection lifecycle | CMS-React/docs/modules.md; recruitment audit | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-042 | Recruitment | Recruitment | Applicant audit | Process log | Read-only status-change audit trail | CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-043 | Recruitment | Recruitment | Recruitment security | Jobs.View authorization | Source finding: secure GetVacancyById authorization | memory QA audit | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | Critical | Unassigned |  |  |  | Isolated integration proof required | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-044 | Recruitment | Recruitment | Public application | Anonymous apply and resume upload | Public applicant submission/upload security | AccountController.cs; ApplicantsController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-045 | Public Careers | Public Careers | Career profile | Company career content | Company profile / public career configuration | CareerProfileController.cs; PublicCompanyProfileController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-046 | Public Careers | Public Careers | Public jobs | Company job catalog | Public jobs, job detail and URL slug/code lookup | PublicCareerController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-047 | Public Careers | Public Careers | Public applications | Apply and resume upload | Public application reference and resume submission | PublicCareerController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-048 | Public Careers | Public Careers | Candidate engagement | Saved jobs and company follows | Anonymous saves, follows and preferences | PublicCareerEngagementController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-049 | Public Careers | Public Careers | Subscriptions | Job alerts | Subscribe, verify, preference, unsubscribe | PublicCareerSubscriptionController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-050 | Offboarding | Offboarding | Exit initiation | Employee resignation | Self-service resignation start and case | CMS-React/docs/offboarding-ui-doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-051 | Offboarding | Offboarding | Exit management | HR/manager case management | Management review and state decisions | EmployeeService.cs; offboarding-ui-doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-052 | Offboarding | Offboarding | Operational clearance | Handover, assets, access, finance, benefits | EmployeeExitOperationsPanel.tsx; offboarding-ui-doc.md | High | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium |  | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-053 | Offboarding | Offboarding | Exit policy | Company exit policy and templates | Admin policy / clearance templates | EmployeeExitPolicySettings.tsx; offboarding-ui-doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-054 | Offboarding | Offboarding | Exit negotiation | Notice adjustment and discussion | Awaiting employee decision / discussion actions | README_OFFBOARDING_FIXES.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-055 | Offboarding | Offboarding | Former employee portal | Secure post-exit portal | OTP, case, documents and requests | PublicFormerEmployeePortalController.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-056 | Offboarding | Offboarding | Rehire | Rejoin employee | Eligible rehire decision and reactivation | offboarding-ui-doc.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-057 | Offboarding | Offboarding | Offboarding delivery gap | Frontend contract wiring | New status and cancel endpoint verification | README_OFFBOARDING_FIXES.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-058 | Calendar & Policies | Calendar & Policies | Calendar | Holiday calendar | Holiday/event administration and leave/dashboard data | CalendarController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-059 | Calendar & Policies | Calendar & Policies | Working schedule | Office schedules and weekly off | Effective schedule, weekly off, company working calendar | EffectiveOfficeScheduleService.cs; WeeklyOffService.cs | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-060 | Calendar & Policies | Calendar & Policies | Policies | Company policy lifecycle | Company policies and route authorization review | CMS-React/docs/routing-and-auth.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-061 | Operations | Operations | Dashboard | Operational KPIs | Headcount, applications, notices, leave, positions | DashboardController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-062 | Operations | Operations | Notices | Notice board | Company announcements and dashboard widget | NoticeBoardController.cs; CMS-React/docs/modules.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Medium | Low | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-063 | Quality Engineering | Quality Engineering | Playwright QA | End-to-end regression | Multi-project local QA harness | CMS-QA/README.md; memory evidence | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-064 | Quality Engineering | Quality Engineering | API / service tests | Backend automated tests | Service/API test projects | Codeji.CMS.Services.Tests.csproj; README.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | High | Medium | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-065 | Quality Engineering | Quality Engineering | High-risk testing | Isolated integration scenarios | Tenant, payroll, leave, upload and auth scenarios | backend doc.md; memory QA audit | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | Critical | Unassigned |  |  |  | Isolated integration proof required | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-066 | DevOps & Security | DevOps & Security | Deployment | Secrets and config | JWT, MongoDB, SMTP and third-party secret handling | backend README.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-067 | DevOps & Security | DevOps & Security | Database operations | MongoDB replicas and backup | Replica set, backup and restore readiness | backend README.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
HRMS-068 | DevOps & Security | DevOps & Security | Release assurance | Production release checks | Backend/frontend checks and tenant/public flow verification | backend README.md | Feature | 75 | 75 | 75 | 65 | 50 | 25 | 25 | 50 | 55 |  | Auto | 55 | In Progress | Needs QA | Critical | High | Unassigned |  |  |  | Define runtime acceptance test | Source mapped; runtime validation required | Documented - Not Runtime Verified | 46268
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification
[7 empty] | Feature | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Auto |  | Not Started | Not Ready | Medium | Medium | Unassigned | [6 empty] | Unknown / Needs Verification

## Module Summary
Module Summary — live feature, progress and readiness rollup
Module | Feature Items | Effective % | Auto % | Manual Mode | Blocked | Critical | Needs QA | Production Ready | Overdue | Next Management Move
Platform & Access | 5 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 5 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Company & Tenant | 4 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 1 | 4 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Employees | 5 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 5 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Leave | 5 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 5 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Attendance | 7 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 1 | 7 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Work From Home | 5 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 5 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Payroll | 7 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 7 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Recruitment | 6 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 1 | 6 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Public Careers | 5 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 5 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Offboarding | 8 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 8 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Calendar & Policies | 3 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 3 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Operations | 2 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 2 | 0 | 0 | Review blockers, owner, target date and runtime evidence
Quality Engineering | 3 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 1 | 3 | 0 | 0 | Review blockers, owner, target date and runtime evidence
DevOps & Security | 3 | e.reduce is not a function | e.reduce is not a function | 0 | 0 | 0 | 3 | 0 | 0 | Review blockers, owner, target date and runtime evidence
| 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
| 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
| 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Overdue = COUNTIFS('Master Feature Tracker'!$T4:T303,">0",'Master Feature Tracker'!$B4:B303,[Module],'Master Feature Tracker'!$AA4:AA303,"<>",'Master Feature Tracker'!$AA4:AA303,"<"&TODAY(),'Master Feature Tracker'!$U4:U303,"<>Done")

## Layer Readiness
Layer Readiness — live delivery completeness by engineering layer
Layer | Average % | 0% | 25% | 50% | 75% | 100% | Management Interpretation
UI | 75 | 0 | 0 | 0 | 68 | 0 | User experience availability
API | 75 | 0 | 0 | 0 | 68 | 0 | API/service implementation
Database | 75 | 0 | 0 | 0 | 68 | 0 | Persistence and data migration
Business Rules | 65 | 0 | 0 | 0 | 0 | 0 | Workflow correctness
Security | 50 | 0 | 0 | 68 | 0 | 0 | Authorization, tenant safety and abuse protection
Integrations | 25 | 0 | 68 | 0 | 0 | 0 | External systems / email / files / PDF
QA | 25 | 0 | 68 | 0 | 0 | 0 | Automated and runtime validation
Documentation | 50 | 0 | 0 | 68 | 0 | 0 | Runbooks, code-aligned documentation and evidence

## Roadmap Priorities
Roadmap & Priorities — update as product direction is agreed
Sequence | Theme | Objective | Priority | Entry Criteria | Exit Evidence | Dependencies / Risks | Target Release | Owner | Status | Target Date | Notes
1 | Production foundation | Prove tenant, security, backup and release baseline | Critical | Safe test environment and named owner | Tenant E2E + backup restore evidence | No approved isolated Testing database | R1 | Unassigned | Planned |  | Do not rely only on source evidence
2 | Core HR assurance | Prove leave / attendance / WFH / payroll workflows under failure | Critical | R1 accepted | Integration and concurrency scenarios pass | Multi-document transaction/saga decision | R2 | Unassigned | Planned |  | Prioritize workflow safety over new scope
3 | Offboarding release | Complete documented frontend/API contract verification | High | Contract reviewed | UI status/actions and portal security regression | New status/endpoint wiring | R2 | Unassigned | Planned |  | Use current offboarding docs as evidence
4 | Recruitment governance | Close authorization and transition-matrix gaps | High | Security acceptance defined | Role and public-upload test matrix passes | Workflow owner and test environment | R3 | Unassigned | Planned |  | Source findings require runtime confirmation
5 | Modular onboarding MVP | Registration, setup stepper and entitlement model | High | ADR + UX prototype approved | Pilot company completes guided setup | Packaging, billing and entitlement decisions | R4 | Unassigned | Planned |  | Vision; not current implementation

## Future Vision
Future Vision & Product Ideas — explicit ideas, not current-state claims
Idea ID | Theme | Opportunity | Customer Value | MVP | Enterprise Extension | Key Data / API Need | Security / Tenant Requirement | Success Metric | Priority | Status | Owner | Decision / Next Step
FV-001 | Modular product | Tenant-selected modules and features | Fit small and large organisations without irrelevant UI | Module catalog + entitlement records | Contract/billing and delegated admin controls | TenantModule, FeatureEntitlement, capability map | Server-enforced entitlement checks | Activation by selected module | High | Planned | Unassigned | Approve packaging and entitlement ADR
FV-002 | Onboarding | Registration-to-live guided stepper | Faster time to first value | Profile, module selection, role setup, checklist | SSO/domain verification and multi-admin setup | OnboardingSession, checklist evidence | Admin-only setup, tenant isolation | Onboarding completion rate | High | Planned | Unassigned | Prototype 3 company-size journeys
FV-003 | Configurable UI | Relevant menu/dashboard/forms per company | Less noise; clearer adoption | Capability-driven navigation and cards | Role/department dashboards and templates | Capability map and configuration version | Never rely on client-only hiding | Feature adoption and support volume | High | Planned | Unassigned | Design API contract
FV-004 | Workflow resilience | Transaction/saga/outbox for multi-document HR flows | Prevent partial approvals and payroll errors | Leave-to-attendance recovery path | Reusable orchestration/audit/outbox platform | Workflow event / outbox records | Idempotency, audit and retry controls | Recovery time / failed workflow incidents | Critical | Planned | Unassigned | Architecture spike and ADR

## Company Onboarding Vision
Company Modular Onboarding — registration → modal stepper → selected capabilities
Step | Journey Stage | User Action | System / Data | Module / Feature Choice | Security & Governance | Small Company Default | Large Company Option | Done When | Status | Priority | Open Product Decision
1 | Registration | Company/admin registers and verifies contact | Tenant provision record + onboarding session | Core HR starter pack | Rate limit, verification, unique tenant boundary | Company profile + employees | SSO/domain verification | Tenant and session created | Planned | Critical | Verification and approval model
2 | Welcome stepper | Admin resumes guided modal | Persistent step/skip/resume state | Select business size and required modules | Only authorized tenant admin configures | 3–5 essential setup steps | Delegated admins / procurement | Resumable across devices | Planned | High | Can a step be skipped?
3 | Module selection | Choose modules/features | Module catalog + selected entitlements | Employees, leave, attendance | Server denies unentitled API/action | Opinionated core pack | Payroll, careers, recruitment, offboarding | Selections audited and versioned | Planned | High | Commercial packaging/trial
4 | Configuration | Set roles, policies, schedules | Tenant config version + validation | Policies/workflows/forms | Role-scoped writes and audit | Default policy templates | Department/role-specific policies | Configuration passes readiness checks | Planned | High | Change/migration policy
5 | Configured UI | Use tailored workspace | Capability map feeds navigation/dashboard | Visible menus/cards/actions | Server and UI enforce same capability map | Simplified navigation | Role/department workspaces | No unentitled path usable | Planned | High | Dependency display strategy
6 | Go live | Confirm readiness | Checklist evidence and attestation | Enable selected modules | Audit record + release approval | Basic readiness checklist | Integration/security readiness pack | Readiness recorded | Planned | Medium | What is mandatory?
7 | Change later | Add/remove scope responsibly | Effective-dated entitlement change | Add modules/features later | Approval, audit, migration safeguards | Self-service additions | CSM/contract approval path | Change is auditable/reversible | Planned | Medium | Billing and data retention

## Bugs & Tech Debt
Bugs, Technical Debt & Dependencies — actionable and evidence-labelled
ID | Type | Area | Finding / Gap | Impact | Severity | Status | Evidence | Verification | Mitigation / Next Action | Owner | Target Date | Release | Blocks Release?
TD-001 | Architecture | Leave / Attendance / Payroll | Multi-document writes lack demonstrated transaction/session atomicity | Partial state under failure | Critical | Open | Memory-backed audit | Documented - Not Runtime Verified | Choose transaction/saga/outbox and run recovery tests | Unassigned |  | R2 | Yes
TD-002 | Test Gap | Payroll | Concurrent generation/process/edit scenario not executed | Incorrect processing state | Critical | Open | backend doc.md | Documented - Not Runtime Verified | Run isolated concurrency test | Unassigned |  | R2 | Yes
BUG-001 | Source Finding | Authentication | Refresh 401 can deadlock queued requests | Users stuck after token failure | High | Open | QA-BUG-REPORT-4 reference | Documented - Not Runtime Verified | Reproduce, patch, add regression | Unassigned |  | R1 | Yes
BUG-002 | Source Finding | Recruitment | GetVacancyById lacks Jobs.View authorization | Unauthorized access risk | High | Open | QA-BUG-REPORT-4 reference | Documented - Not Runtime Verified | Add authorization and role matrix test | Unassigned |  | R3 | Yes
TD-003 | Security / Test Gap | Tenant isolation | Cross-company employee/profile proof pending | Data-isolation assurance gap | Critical | Open | backend doc.md | Documented - Not Runtime Verified | Two-company isolated test matrix | Unassigned |  | R1 | Yes
TD-004 | Delivery Gap | Offboarding | New status and endpoint UI wiring needs verification | Workflow inconsistency | High | Open | README_OFFBOARDING_FIXES.md | Documented - Not Runtime Verified | Verify contract/UI + regression | Unassigned |  | R2 | Yes
TD-005 | Product Architecture | Modular onboarding | No entitlement/capability model in current source scan | Cannot safely deliver configurable HRMS | High | Open | Product vision request | Unknown / Needs Verification | ADR + data model spike | Unassigned |  | R4 | No

## Releases Milestones
Releases & Milestones — evidence-based release control
Release | Objective | Scope | Entry Criteria | Exit Criteria | Readiness | Target Date | Actual Date | Owner | Status | Risk / Blocker | Evidence
R1 — Foundation | Prove operating safety | Tenant, auth, secrets, backup/restore | Named isolated test environment | Evidence links and no critical unresolved blocker | Not Ready |  |  | Unassigned | Planned | No approved test DB | Attach test and restore evidence
R2 — Core HR | Harden critical workflows | Leave, attendance, WFH, payroll, offboarding | R1 accepted | Integration/concurrency and regression pass | Not Ready |  |  | Unassigned | Planned | Transaction/recovery design unresolved | Tracker + test report
R3 — Recruitment | Govern recruitment | Authorization, pipeline, public applications | Acceptance matrix defined | Role/public upload regression passes | Not Ready |  |  | Unassigned | Planned | Workflow decision pending | Security report
R4 — Modular Onboarding MVP | Validate configurable product | Registration, stepper, entitlement map | ADR/prototype approved | Pilot tenant completes onboarding | Not Ready |  |  | Unassigned | Planned | Packaging and capability model unresolved | Pilot evidence

## Definitions Dropdowns
Definitions & Dropdown Lists — update the lists to govern future entries
Status | Priority | Readiness | Risk | Progress Mode | Layer Score | Owner | Verification | Feature Type | Change Type
Not Started | Critical | Not Ready | Critical | Auto | 0 | Unassigned | Verified - Source | Feature | Baseline
Planned | High | In Build | High | Manual | 25 | Product | Documented - Not Runtime Verified | Sub-feature | Progress Update
In Progress | Medium | Needs QA | Medium |  | 50 | Backend | Runtime Verified | Workflow | Scope Change
Blocked | Low | Pilot Ready | Low |  | 75 | Frontend | Unknown / Needs Verification | Integration | Bug Update
Ready for QA |  | Production Ready |  |  | 100 | QA |  | Security Control | Release Update
Done | [5 empty] | DevOps |  | Test Case | Decision
Deferred | [5 empty] | HR / Ops |  | Technical Debt

## Change Log
Change Log — maintain auditability of every material tracker update
Change ID | Date | Changed By | Tracker ID / Sheet | Change Type | Before | After | Reason / Decision | Evidence / Link | Follow-up
CL-001 | 2026-09-03 | Codex | Workbook rebuild | Baseline | Static broad module rows | Feature-level dynamic auto/manual model | Rebuilt after usability feedback | Source/docs scan | Assign owners, dates and runtime evidence
CL-002
CL-003