## Dashboard
HRMS Delivery Command Center
Live formulas update when the Master Feature Tracker is edited. Empty dates and owners are intentional editable placeholders.
Overall progress |  | Tracked features |  | Blocked |  | Needs QA |  | Not ready |  | Critical / High
64.17% |  | 18 |  | 0 |  | 16 |  | 2 |  | 15
Status | Count | Priority | Count |  | Production readiness | Count | Layer | Count | Overdue
Not Started | 0 | Critical | 6 |  | Not Ready | 2 | Full stack | 14 | 0
Planned | 2 | High | 9 |  | In Build | 0 | Backend/API + UI | 2 | Set target dates to activate this KPI
In Progress | 16 | Medium | 3 |  | Needs QA | 16 | Testing | 1
Blocked | 0 | Low | 0 |  | Pilot Ready | 0 | Platform | 1
Ready for QA | 0 |  |  |  | Production Ready | 0
Done | 0
Deferred | 0
Update discipline: assign Owner, Target Date, Next Action and Release in Master Feature Tracker. Use Unknown / Needs Verification until observed in a safe runtime environment.

## Master Feature Tracker
Master Feature Tracker — editable source of truth
ID | Module | Feature | Sub-feature / Scope | Layer | UI | Backend / API | Database | Business Rules | Permissions / Security | Integrations | Testing | Documentation | Bugs / Dependencies | Owner | Priority | Status | % Complete | Production Readiness | Start Date | Target Date | Release / Milestone | Risk | Blocker | Next Action | Technical Debt | Notes | Evidence / Source | Verification
AUTH-001 | Platform & Access | Authentication | JWT login, bootstrap, token refresh | Backend/API + UI | Present | Present | MongoDB users | Session bootstrap | JWT + role/module gates | Email | Needs regression | routing-and-auth.md | Refresh queue source finding | Unassigned | Critical | In Progress | 65% | Needs QA |  |  | Security hardening | High | Refresh-token concurrency | Reproduce/patch queue behavior | Token refresh race | Source audit finding; runtime not verified | CMS-React/docs/routing-and-auth.md; backend doc.md | Documented - Not Runtime Verified
COMP-001 | Company & Tenant | Company management | Company profile and tenant context | Full stack | Present | Present | MongoDB Company | Company-scoped data | Tenant claims + server checks | Public careers | Needs E2E | README.md | Cross-tenant matrix pending | Unassigned | Critical | In Progress | 70% | Needs QA |  |  | Tenant safety | High | Isolated tenant test unavailable | Run two-company IDOR matrix | Tenant enforcement proof gap | Do not mark production-ready until integration proven | backend README.md; doc.md | Documented - Not Runtime Verified
EMP-001 | Employees | Employee lifecycle | Create, profile, employment status | Full stack | Present | Present | MongoDB employee | Employment state | Employees permissions | Email | Needs E2E | routing-and-auth.md | Cross-company profile test pending | Unassigned | High | In Progress | 70% | Needs QA |  |  | Core HR | High | Isolated test DB | Verify profile IDOR and status | E2E coverage gap | Feature presence confirmed; behavior not fully runtime-tested | CMS-React/docs/routing-and-auth.md; backend doc.md | Documented - Not Runtime Verified
LEAVE-001 | Leave | Leave management | Request, approval, balance | Full stack | Present | Present | MongoDB leave | Approval/reconciliation | ModulePermissionAttribute | Notifications | Needs integration | leave-attendance-payroll flow | Multi-document atomicity | Unassigned | Critical | In Progress | 75% | Needs QA |  |  | HR core | High | No transaction/saga proof | Test partial failure and concurrency | Multi-document workflow | Approved leave creates source-linked attendance per docs | memory-backed docs: leave/attendance/payroll | Documented - Not Runtime Verified
ATT-001 | Attendance | Attendance calendar | Status, manual actions, source-owned records | Full stack | Present | Present | MongoDB attendance | Source ownership and locked periods | Attendance permissions | Calendar | Needs integration | leave-attendance-payroll flow | Lock/correction race test pending | Unassigned | Critical | In Progress | 75% | Needs QA |  |  | HR core | High | Isolated test DB | Run locked attendance regression | Reopen/relock audit | Source-owned WFH/leave rows require dedicated correction | backend services/controllers; memory summary | Verified - Source
ATT-002 | Attendance | Working calendar | Company schedule, weekly off, holidays | Backend/API + UI | Present | Present | MongoDB settings | Effective office schedule | Company scoped | None | Needs integration | README.md | Calendar edge-case verification | Unassigned | High | In Progress | 65% | Needs QA |  |  | HR core | Medium | Test calendar cases | Test date/timezone policy | Date handling coverage | Company calendar services are present | CompanyWorkingCalendarService.cs | Verified - Source
WFH-001 | Work From Home | WFH requests | Approval and attendance linkage | Full stack | Present | Present | MongoDB WFH | Source-owned attendance | Dedicated correction authorization | None | Needs E2E | modules.md | Generic edit protection needs regression | Unassigned | High | In Progress | 70% | Needs QA |  |  | HR core | High | Runtime test pending | Verify generic edit rejects source-owned row | Correction workflow coverage | Server-side source ownership documented | WorkFromHomeController.cs; memory summary | Verified - Source
PAY-001 | Payroll | Payroll processing | Periods, processing, payslips | Full stack | Present | Present | MongoDB payroll | Locked attendance dependency | Payroll permissions | PDF | Needs concurrency | README.md | Generation/process race pending | Unassigned | Critical | In Progress | 70% | Needs QA |  |  | Payroll hardening | Critical | Isolated test DB | Run concurrent generation/edit test | Revision/audit design | Production readiness blocked by concurrency validation | PayRollController.cs; doc.md | Documented - Not Runtime Verified
PAY-002 | Payroll | Payroll settings | Divisor policy and salary setup | Full stack | Present | Present | MongoDB settings | Period rules | PayrollSettings permission | None | Needs QA | routing-and-auth.md | Config E2E pending | Unassigned | High | In Progress | 65% | Needs QA |  |  | Payroll hardening | Medium | QA scenario pending | Validate policy changes against payroll | Settings versioning | Controllers/services confirmed in source | PayrollDivisorPolicyController.cs; SalaryController.cs | Verified - Source
REC-001 | Recruitment | Job vacancy | Jobs and candidate pipeline | Full stack | Present | Present | MongoDB jobs/applicants | Pipeline transitions | Jobs.View gap source finding | Email, resume upload | Needs security test | recruitment audit | Unenforced transition matrix | Unassigned | High | In Progress | 60% | Needs QA |  |  | Recruitment controls | High | Authorization and workflow matrix | Protect read endpoint; define transitions | Pipeline governance | Source audit finding; not runtime confirmed | JobVacancyController.cs; memory recruitment audit | Documented - Not Runtime Verified
REC-002 | Recruitment | Public application | Apply job and upload resume | Full stack | Present | Present | MongoDB applicant/resume | Anonymous submission | Upload abuse/tenant testing | Email | Needs security test | README.md | Public cId matrix pending | Unassigned | High | In Progress | 55% | Needs QA |  |  | Recruitment controls | High | Isolated test environment | Run public-tenant and upload tests | Rate limit / malware scan TBD | Endpoints exist; exact protection needs verification | ApplicantsController.cs; doc.md | Documented - Not Runtime Verified
CAREER-001 | Public Careers | Career portal | Company code, jobs, branding | Full stack | Present | Present | MongoDB company/career profile | Publish and active checks | Anonymous public guards | Public API | Needs browser/API | README.md | Profile publish state E2E pending | Unassigned | Medium | In Progress | 70% | Needs QA |  |  | Public careers | Medium | Runtime public flow test | Verify published/disabled company/job matrix | Public content governance | CareerPortalEnabled and publish guards documented | PublicCareerController.cs; README.md | Documented - Not Runtime Verified
OFF-001 | Offboarding | Exit lifecycle | Resignation, HR/manager case management | Full stack | Present | Present | MongoDB EmployeeExit | State machine and clearances | Company isolation / role-aware actions | Former employee portal | Needs regression | offboarding-ui-doc.md | Frontend update explicitly needed for new status | Unassigned | High | In Progress | 75% | Needs QA |  |  | Offboarding release | High | Wire new status + endpoint | Verify AwaitingEmployeeNoticeOffer UI/API | Status wiring | 11 backend fixes documented; UI follow-up noted | README_OFFBOARDING_FIXES.md; offboarding-ui-doc.md | Documented - Not Runtime Verified
OFF-002 | Offboarding | Former employee portal | Secure documents and requests | Full stack | Present | Present | MongoDB portal/request | Post-exit access rules | Scoped secure access | Email | Needs security test | offboarding-ui-doc.md | Invite/access expiry runtime test | Unassigned | High | In Progress | 65% | Needs QA |  |  | Offboarding release | High | Security test environment | Test expired/cross-user access | Access lifecycle proof | Source documents describe separate secure flow | PublicFormerEmployeePortalController.cs; offboarding-ui-doc.md | Documented - Not Runtime Verified
POL-001 | Policies & Admin | Company policies | Policy routes and governance | Full stack | Present | Present | MongoDB policies | Policy lifecycle | Policy permission needs route review | None | Needs regression | routing-and-auth.md | Parent route may be unguarded | Unassigned | Medium | Planned | 45% | Not Ready |  |  | Route hardening | Medium | Route authorization decision | Add/confirm route gate | Route consistency | Docs identify companypolicy parent as potential guard gap | CMS-React/docs/routing-and-auth.md | Verified - Source
DASH-001 | Dashboard & Notices | Dashboard | Operational summaries and notices | Full stack | Present | Present | MongoDB/read models | Company context | Dashboard permission | None | Needs E2E | architecture.md | No current runtime evidence | Unassigned | Medium | In Progress | 55% | Needs QA |  |  | Operational visibility | Medium | Define acceptance KPIs | Validate tenant-scoped metrics | Read-model test coverage | Controllers/services are present | DashboardController.cs; NoticeBoardController.cs | Verified - Source
QA-001 | Quality Engineering | Automated QA harness | Playwright regression suite | Testing | N/A | N/A | Test artifacts | Test isolation | Credential handling | Playwright | Partial suite results | CMS-QA README | Local shared rate limiter can cause 429 | Unassigned | High | In Progress | 70% | Needs QA |  |  | Quality gate | High | Stabilize isolated run | Run full suite with safe config | Environment coupling | Prior observed guarded localhost run 87 pass, 0 fail, 3 skip | CMS-QA/README.md; memory summary | Documented - Not Runtime Verified
OPS-001 | DevOps & Security | Production readiness | Secrets, backups, replica set, deployment checks | Platform | N/A | Present | MongoDB | Backups and migration order | Secrets externalized | SMTP/reCAPTCHA | Needs drill | README.md | Restore / E2E evidence unavailable | Unassigned | Critical | Planned | 35% | Not Ready |  |  | Production foundation | Critical | Deployment evidence | Run backup/restore and release checklist | Outbox/transaction architecture | README requires replica set/backups and test flows | backend README.md | Verified - Source

## Module Summary
Module Summary — formula-driven from Master Feature Tracker
Module | Features | Avg % Complete | Done | Blocked | Critical/High | Needs QA | Not Ready | Production Ready | Management Note
Platform & Access | 1 | 65% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Company & Tenant | 1 | 70% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Employees | 1 | 70% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Leave | 1 | 75% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Attendance | 2 | 70% | 0 | 0 | 2 | 2 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Work From Home | 1 | 70% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Payroll | 2 | 67.5% | 0 | 0 | 2 | 2 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Recruitment | 2 | 57.5% | 0 | 0 | 2 | 2 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Public Careers | 1 | 70% | 0 | 0 | 0 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Offboarding | 2 | 70% | 0 | 0 | 2 | 2 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Policies & Admin | 1 | 45% | 0 | 0 | 0 | 0 | 1 | 0 | Update owner, target date and next action in Master Feature Tracker
Dashboard & Notices | 1 | 55% | 0 | 0 | 0 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
Quality Engineering | 1 | 70% | 0 | 0 | 1 | 1 | 0 | 0 | Update owner, target date and next action in Master Feature Tracker
DevOps & Security | 1 | 35% | 0 | 0 | 1 | 0 | 1 | 0 | Update owner, target date and next action in Master Feature Tracker

## Roadmap Priorities
Roadmap & Priorities
Sequence | Theme | Goal | Priority | Target Release | Entry Criteria | Exit / Evidence | Dependencies / Risks | Decision Needed | Owner | Status | Notes
1 | Production foundation | Validate tenant, secrets, backups and release controls | Critical | R1 | Safe isolated test environment | Backup/restore + tenant E2E evidence | No approved isolated DB | Test environment owner | Unassigned | Planned | Derived from README and QA blocker
2 | HR core hardening | Leave, attendance and payroll concurrency / transaction proof | Critical | R2 | Core flows mapped | Concurrency and partial-failure scenarios pass | Multi-document atomicity | Transaction/saga/outbox approach | Unassigned | Planned | Do not claim production-ready before proof
3 | Offboarding completion | Wire documented backend fixes into UI and regression | High | R2 | Status/API contract confirmed | Status rendered + actions pass | Frontend follow-up explicitly documented | Release acceptance | Unassigned | Planned | AwaitingEmployeeNoticeOffer and cancel endpoint
4 | Recruitment governance | Authorization and transition controls | High | R3 | Jobs.View review | API authorization and transition tests pass | Public upload and tenant matrix | Workflow owner | Unassigned | Planned | Source finding; runtime validation required
5 | Company modular onboarding | Registration and selected product configuration | High | R4 | Product decisions signed | Tenant configuration, entitlements and UI gating proven | Licensing/configuration design | Packaging model | Unassigned | Planned | Vision sheet has detailed scope

## Future Vision
Future Vision & Product Ideas — editable product backlog
Vision ID | Theme | Idea / Opportunity | Problem / Customer Value | Target Segment | Hypothesis | Scope / MVP | Success Metric | Priority | Status | Dependencies | Risks / Assumptions | Decision / Next Experiment | Owner
FV-001 | Modular HRMS | Let each company select paid/needed modules and features | Avoid one-size-fits-all HRMS; support small and large companies | SMB, mid-market, enterprise | Configuration improves activation and product fit | Entitlements + module catalog + tenant UI/API gates | Activation, adoption per module, support tickets | High | Planned | Tenant entitlements, billing decision | Complexity / accidental access | Define module catalog and entitlement data model | Unassigned
FV-002 | Guided onboarding | Company registration followed by modal onboarding stepper | Shorten time-to-value and ensure key setup is complete | New tenant admins | Guided setup improves first-week activation | Registration, company profile, module selection, role setup, checklist | Time to configured workspace, completion rate | High | Planned | Onboarding state model | Incomplete configuration / abandonment | Prototype stepper and test with 3 company sizes | Unassigned
FV-003 | Configurable experience | Adapt navigation, dashboard widgets and forms to selected functionality | Keep UI relevant without hiding necessary controls | All tenants | Entitlements + configuration improve usability | Navigation/menu guards, dashboard layout presets, settings | Feature discovery, admin satisfaction | High | Planned | Frontend composition and server guards | Client-only hiding would be insecure | Design server-enforced entitlement contract | Unassigned
FV-004 | Operational assurance | Transaction/saga/outbox for cross-document HR workflows | Prevent partial approvals/processes under failure | All tenants | Durable orchestration reduces HR/payroll risk | Start with leave-to-attendance and payroll | Failed workflow recovery time, incidents | Critical | Planned | Mongo transaction or outbox approach | Migration complexity | Architecture decision record and spike | Unassigned

## Company Onboarding Vision
Company Modular Onboarding — product vision blueprint
Step | Journey Stage | User Experience | System / Data Requirement | Security / Permissions | Small Company Default | Large Company / Enterprise Option | Definition of Done | Status | Priority | Open Question
1 | Company registration | Company creates account and verifies contact | Company + tenant provisioning record; registration state | Rate limit, verification, tenant isolation | Essential company profile | SSO/domain verification / approval | Tenant provisioned safely | Planned | Critical | Who can approve enterprise tenants?
2 | Welcome modal stepper | Admin sees guided modal after registration | Persistent onboarding progress and resumable steps | Only tenant admin can configure | 3–5 essential steps | Expanded setup with delegated admins | Resume works across sessions | Planned | High | Can the stepper be dismissed?
3 | Module selection | Admin selects modules/features appropriate to business | Module catalog, entitlement and selected-feature records | Server authorization based on entitlements | Core HR: employees, leave, attendance | Payroll, recruitment, offboarding, careers, integrations | Selections saved and auditable | Planned | High | Commercial packaging / trial rules?
4 | Feature configuration | Choose policy/form depth, roles, workflows | Tenant configuration versioning | Role-scoped configuration controls | Opinionated defaults | Advanced policy templates and approval chains | Config validated and versioned | Planned | High | Which settings are immutable after go-live?
5 | UI personalization | Only relevant nav, dashboard cards and actions appear | Server-driven UI capability map | Server must deny disabled feature APIs | Simplified navigation | Department/role-specific workspace | UI and API both honor capability map | Planned | High | How are shared dependencies surfaced?
6 | Go-live checklist | Stepper confirms setup, sample data and readiness | Checklist evidence / audit log | Admin attestation, audit trail | Basic readiness checks | Integration and security readiness pack | Readiness state recorded | Planned | Medium | What blocks go-live?
7 | Ongoing change | Admin can add modules/features later | Change request / effective dates / migration | Approval and audit for high-risk changes | Self-service add-ons | Contract/CSM approval workflow | Changes are reversible/auditable | Planned | Medium | Billing and data migration policy?

## Bugs & Tech Debt
Bugs, Technical Debt & Dependencies
ID | Type | Area | Finding / Debt | Impact | Severity | Status | Evidence / Source | Verification | Mitigation / Next Action | Owner | Target Date | Release | Blocker?
TD-001 | Technical Debt | Leave / Attendance | Multi-document workflow lacks demonstrated transaction/session atomicity | Partial updates under failure | Critical | Open | Memory-backed leave/attendance/payroll audit | Documented - Not Runtime Verified | Choose transaction/saga/outbox; integration test failure recovery | Unassigned |  | R2 | Yes
TD-002 | Test Gap | Payroll | Concurrent generation/process/edit race not executed | Incorrect payroll state | Critical | Open | backend doc.md | Documented - Not Runtime Verified | Run isolated concurrency scenario | Unassigned |  | R2 | Yes
BUG-001 | Source Finding | Authentication | Refresh token 401 can deadlock queued requests | Users can be stuck signed out | High | Open | backend doc.md; memory QA audit | Documented - Not Runtime Verified | Reproduce, patch, add regression test | Unassigned |  | R1 | Yes
BUG-002 | Source Finding | Recruitment | GetVacancyById lacks Jobs.View authorization (source audit) | Unauthorized job access | High | Open | memory QA audit | Documented - Not Runtime Verified | Add authorization and test role matrix | Unassigned |  | R3 | Yes
TD-003 | Test Gap | Tenant isolation | Cross-company employee/profile IDOR test needs isolated DB | Data isolation proof gap | Critical | Open | backend doc.md | Documented - Not Runtime Verified | Run two-company E2E matrix | Unassigned |  | R1 | Yes
TD-004 | Delivery Gap | Offboarding | New status/UI and cancel endpoint require frontend wiring verification | Workflow inaccessible or inconsistent | High | Open | README_OFFBOARDING_FIXES.md | Documented - Not Runtime Verified | Verify contract and implement regression coverage | Unassigned |  | R2 | Yes
TD-005 | Architecture | Modular onboarding | No entitlement/configuration model yet | Cannot safely tailor functionality by company | High | Open | Product vision request | Unknown / Needs Verification | Create ADR and configuration model spike | Unassigned |  | R4 | No

## Releases Milestones
Releases & Milestones
Release / Milestone | Objective | Scope | Entry Criteria | Exit Criteria | Readiness | Target Date | Actual Date | Owner | Status | Risks / Blockers | Evidence
R1 — Production foundation | Prove safe baseline | Tenant tests, backup/restore, auth refresh hardening | Isolated test environment approved | Evidence attached; no critical blocker | Not Ready |  |  | Unassigned | Planned | No isolated test DB | Populate evidence links after tests
R2 — HR core hardening | Reduce workflow risk | Leave/attendance/payroll and offboarding completion | R1 baseline accepted | Concurrency / integration pass | Not Ready |  |  | Unassigned | Planned | Atomicity approach unresolved | Master tracker + test report
R3 — Recruitment governance | Control access and pipeline | Jobs authorization, transition matrix, public upload validation | R2 lessons applied | Security matrix and regression pass | Not Ready |  |  | Unassigned | Planned | Workflow decision required | Security test report
R4 — Modular onboarding MVP | Validate configurable product model | Registration, stepper, module selection, capability map | ADR and UX prototype approved | Pilot tenant completes guided setup | Not Ready |  |  | Unassigned | Planned | Packaging/billing/entitlements unresolved | Pilot feedback and audit log

## Definitions Dropdowns
Definitions & Dropdown Lists
Status | Priority | Readiness | Verification | Risk | Owner | Layer | Change Type
Not Started | Critical | Not Ready | Verified - Source | Critical | Product | UI | Feature Update
Planned | High | In Build | Documented - Not Runtime Verified | High | Backend | Backend/API | Status Update
In Progress | Medium | Needs QA | Unknown / Needs Verification | Medium | Frontend | Database | Bug Fix
Blocked | Low | Pilot Ready |  | Low | QA | Security | Release
Ready for QA |  | Production Ready |  |  | DevOps | Integration | Data Correction
Done |  |  |  |  | Unassigned | Testing | Documentation
Deferred | [5 empty] | Business Rule | Future Vision

## Change Log
Change Log — record every meaningful tracker update
Change ID | Date | Changed By | Sheet / Item | Change Type | Before | After | Reason / Decision | Evidence Link / Source | Follow-up
CL-001 | 2026-09-03 | Codex | Initial workbook | Initial Baseline |  |  | Created from code/docs scan; unknowns marked explicitly | Backend README, React docs, QA README | Assign owners/dates and validate runtime evidence
CL-002